SECTION 1 — REPORT IDENTIFICATION

| Report Reference No. | PWD/GJ/RJK/2025-26/0042 | Date of Inspection | 25 May 2025 |
| --- | --- | --- | --- |
| Inspection Type | Routine Field Inspection | Priority | High |
| Division | Rajkot Division – Zone B | Sub-Division | Urban Roads & Bridges |
| Work Order No. | WO/RJK/2025/0189 | File Reference | F.No. MH/RJK/UB/25-26 |

SECTION 2 — TECHNICIAN / OFFICER DETAILS

| Name of Technician | Sh. Ramesh Kumar Patel | Employee ID | PWD-GJ-T-4821 |
| --- | --- | --- | --- |
| Designation | Junior Engineer (Civil) | Grade / Pay Level | Level 6 (₹35,400 – ₹1,12,400) |
| Mobile No. | +91 98765 43210 | Official Email | r.patel@pwd.guj.gov.in |
| Reporting Officer | Sh. D. V. Trivedi, Exe. Eng. | Division Office | PWD Office, Race Course Road, Rajkot |

SECTION 3 — SITE / WORK DETAILS

| Name of Work | Repair & Restoration of Road Surface, Drainage Channels & Culverts along SH-27 (km 14+200 to km 17+500) |
| --- | --- |
| Location / Site | SH-27, Rajkot – Gondal Section, Near Vinzarda Village, Rajkot District, Gujarat – 360 023 |
| GPS Coordinates | 22.3039° N, 70.8022° E (approx.) |
| Length of Section | 3.30 km |
| Type of Work | Road Maintenance – Pothole Patching, Drain Clearing, Culvert Inspection |
| Contractor / Agency | M/s Shreeji Construction Co., Rajkot (Contract No. PWD/GJ/2024-25/RC-081) |

SECTION 4 — SITE CONDITIONS AT TIME OF INSPECTION

| Weather Conditions | Clear / Sunny | Temperature (°C) | 37°C |
| --- | --- | --- | --- |
| Time of Inspection | 09:30 AM – 01:15 PM | Traffic Condition | Moderate (Mixed Traffic) |
| Visibility | Good | Safety Measures in Place | Cones & Warning Boards Deployed |

SECTION 5 — TECHNICAL INSPECTION CHECKLIST

A. Road Surface & Pavement

| ✓ / ✗ | Inspection Item |
| --- | --- |
| [✓] | Pothole identification and mapping completed |
| [✓] | Pothole depth measured (average depth: 8 cm) |
| [✓] | Bitumen mix grade verified as per specification (VG-30) |
| [✓] | Compaction test (proctor) results within acceptable limits |
| [✓] | Edge restraint and shoulder condition checked |
| [ ] | Road markings and reflective studs inspected |
| [ ] | Skid resistance (BPN value) measured at 3 locations |

B. Drainage & Culverts

| [✓] | Drain cross-section dimensions verified as per DPR |
| --- | --- |
| [✓] | Silting / debris accumulation measured and recorded |
| [✓] | Culvert inlet and outlet conditions assessed |
| [✓] | RCC culvert barrel crack survey completed (3 culverts) |
| [ ] | Hydraulic adequacy of culvert checked |
| [✓] | Retaining wall stability observed |

C. Safety & Compliance

| [✓] | Contractor's safety plan reviewed and acknowledged |
| --- | --- |
| [✓] | PPE usage by labourers verified |
| [✓] | Material storage compliant with IS specifications |
| [✓] | Environment Protection measures in place |
| [ ] | Night-time signage verified |

SECTION 6 — OBSERVATIONS & FIELD MEASUREMENTS

| S.No. | Description of Defect / Observation | Chainage (km) | Severity | Recommended Action |
| --- | --- | --- | --- | --- |
| 1 | Extensive potholes – multiple clusters, avg. area 0.8 m², depth 8 cm | km 14+300 – 14+700 | HIGH | Immediate hot-mix patching & compaction |
| 2 | Left side drain blocked with silt & debris over approx. 220 m stretch | km 15+100 – 15+320 | MODERATE | Manual desilting within 7 days |
| 3 | Hairline cracks observed in RCC culvert barrel (C-3), span 3.5 m | km 16+020 | MODERATE | Structural assessment & crack grouting |
| 4 | Road shoulder erosion – width loss ~1.2 m on right side | km 17+100 – 17+500 | LOW | Shoulder reconstruction in next cycle |

SECTION 7 — MATERIALS & EQUIPMENT DEPLOYMENT

| S.No. | Item Description | Unit | Qty. Deployed | Qty. Verified |
| --- | --- | --- | --- | --- |
| 1 | BC (Bituminous Concrete) Hot Mix – VG-30 | MT | 12.50 | 12.50 ✓ |
| 2 | Emulsion (CSS-1) – Prime Coat | Litre | 320 | 305 ✓ |
| 3 | Plate Compactor (1.5 MT) | Nos. | 2 | 2 ✓ |
| 4 | Excavator / JCB for drain cleaning | Nos. | 1 | 1 ✓ |
| 5 | Skilled Labour (Masons, Helpers) | Nos. | 18 | 15 ⚠ |

SECTION 8 — PHOTOGRAPHIC EVIDENCE

| S.No. | Description | Photo Reference / Filename |
| --- | --- | --- |
| 1 | Overview of pothole cluster – Ch. 14+350 | RJK_SH27_25MAY25_001.JPG |
| 2 | Depth measurement of pothole (8 cm) with scale | RJK_SH27_25MAY25_002.JPG |
| 3 | Silt-blocked drain – Ch. 15+200 | RJK_SH27_25MAY25_003.JPG |
| 4 | Hairline crack in culvert barrel – Ch. 16+020 | RJK_SH27_25MAY25_004.JPG |
| 5 | Road shoulder erosion – Ch. 17+350 | RJK_SH27_25MAY25_005.JPG |

Note: All photographs geotagged with timestamp and stored in official PWD Photo Repository under File Ref: F.No. MH/RJK/UB/25-26.

SECTION 9 — SUMMARY & RECOMMENDATIONS

Overall Site Assessment: The inspection of SH-27 from km 14+200 to 17+500 reveals significant pavement distress primarily in the form of potholes between km 14+300–14+700, warranting urgent remedial action before the monsoon onset. Drainage infrastructure is partially compromised due to silting. The RCC culvert at km 16+020 requires immediate structural assessment. Contractor resource mobilisation is below the contractually stipulated levels (15 labourers vs. 18 sanctioned) and must be rectified within 48 hours. Recommended Actions: 1. Issue Stop-Work Notice to contractor for under-mobilisation of resources and seek compliance within 48 hours. 2. Commence pothole patching works from km 14+300 with priority before 31 May 2025. 3. Engage structural consultant for culvert crack assessment within 10 working days. 4. Complete drain desilting before onset of South-West Monsoon (target: 10 June 2025). 5. Follow-up inspection to be scheduled within 15 days.

SECTION 10 — DECLARATIONS & SIGNATURES

I, the undersigned, certify that the above inspection was carried out personally and that the details reported herein are true and accurate to the best of my knowledge and belief.

| Prepared By: Sh. Ramesh Kumar Patel Junior Engineer (Civil), PWD-GJ-T-4821 Date: 25 / 05 / 2025 | Verified & Approved By: Sh. D. V. Trivedi Executive Engineer (Civil), PWD Rajkot Division Date: __ / __ / 2025 Seal: |
| --- | --- |

For Office Use Only — Acknowledgement / Diary Number: PWD/GJ/RJK/DIV-B/ACK/__________ Date Received: __ / __ / 2025